## Home
SAM QIP Team Workbook
One shared file for the whole project — save it on the team drive / Teams and everyone edits the same copy. Do not email versions.
PROJECT
Project title | Enter…
SMART aim | To increase/reduce [measure] from [X] to [Y] by [date]…
WHO quality domain targeted | Pick from dropdown →
Ward / setting | Enter…
Project lead | Enter…
Consultant supervisor | Enter…
Team members | Enter…
Key stakeholders — who must say yes? | Ward manager, pharmacy, IT… name them before you launch
Audit registration no. & date | Register BEFORE baseline — enter no. here
Project type | Pick from dropdown →
Project start date | Enter…
Intervention start date | Enter…
Current stage | Pick from dropdown →
YOUR PITCH & FIRST CHANGE (Stages 1–2) | Draft it at aimqa.github.io/SAMQIP — Pitch and 2×2 tabs — then paste the final wording here.
1 The problem | What’s going wrong, for which patients — as you’ve seen it on the ward…
2 The number | One honest local figure: “12 of 20 charts last week”…
3 The aim | From [X] to [Y] by [date] — same as the SMART aim above…
4 Why it matters | The WHO quality domain it targets — and what it means for patients…
5 The ask | A named supervisor — and a ‘yes, go ahead’ to collect baseline data…
Root cause (from 5 Whys) | The system cause you stopped at — a process, a form, a step; not a person…
Change idea for cycle 1 | Your quick win: high impact, low effort — top-left of the 2×2…
AT A GLANCE (updates itself)
0 of 7 stages done
0 open actions
1 data points on the run chart
0 of 18 SQUIRE items covered
Draw your process map & driver diagram → aimqa.github.io/SAMQIP
SAM QIP Diagram Tool — WHO quality lens built in · worked VTE example · export the PNG straight into your slides
HOW TO USE THIS WORKBOOK
– White bordered cells and grey ‘Enter…’ text are yours to overwrite.
– Grey italic EXAMPLE rows show the expected format — overwrite or delete them.
– Cells with a dropdown show an arrow when clicked — pick, don’t type.
– One tab per job: Stages — where the project is · Actions Log — who’s doing what · Process Map — what actually happens · Causes — why it happens · Data Plan — the three measures · Data Log — the run chart · Diary — the words · PDSA Log — one row per cycle · SQUIRE Check — before you present · Share & Replicate — hand it on to another ward or trust.
– New team member? Read the SAM QIP Roadmap deck first — this workbook follows its seven stages.
– Draw it in the tool, track it here: process maps, 5 Whys, driver diagrams and the 2×2 are built at aimqa.github.io/SAMQIP; this workbook holds the decisions, the data and the write-up. Paste the tool’s PNGs into your slides.
– WHO quality lens — quality services are effective · safe · people-centred · timely · equitable · integrated · efficient. Your aim should target at least one.
– Count, don’t name — no patient-identifiable data in this workbook. If your project is research rather than QI or audit, it needs HRA/REC approval before you start.
Source: WHO — Quality of care (who.int/health-topics/quality-of-care)

## Stages
Stage Tracker — the seven stages
Update Status as you go — Home counts the ‘Done’ rows. ‘You’re done when…’ is the exit test from the Roadmap.
# | Stage | You’re done when… | Owner | Status | Target date | Completed | Notes / link
1 | Pitch Your QIP | A consultant has said ‘yes’ — named supervisor, project type settled (QI / audit / research), stakeholders spoken to |  | Not started
2 | Plan Your QIP | Baseline run chart + one-page data plan (and project registered) |  | Not started
3 | Plan Your Intervention | The team knows the plan and the start date is in the diary |  | Not started
4 | Deliver & Measure | 6–8 post-change data points + a project diary |  | Not started
5 | Present Your Data | The team has seen the chart and agreed keep / tweak / drop |  | Not started
6 | The SQUIRE Write-Up | All 18 items ticked (or justified) — and submitted |  | Not started
7 | Repeat the Cycle | Cycle 2 has an owner and a start date — even if it isn’t you |  | Not started

## Actions Log
Actions & Decisions Log — the team’s conversation, in one place
Add a row instead of sending a WhatsApp — anyone opening the file sees who’s doing what. Overdue open actions turn red.
Date | Type | Raised by | Detail | Owner | Due | Status | Closed
2026-01-12 | Action | A. Khan (FY1) | EXAMPLE — print 50 updated clerking proformas and restock the admissions trolley | B. Patel (SHO) | 2026-01-19 | Done | 2026-01-16

## Process Map
Process Map — what actually happens, step by step
Stage 2. Walk the route with the people who do the work — map what happens, not what the policy says. Flag where it goes wrong: those steps become your change ideas.
# | What happens (one line) | Who does it | Typical time (mins) | Waiting before this step (mins) | Problem here? | What goes wrong | Idea to fix it → driver diagram | AT A GLANCE (updates itself)
EX | Drug chart written | Admitting doctor | 10 | 45 | Yes | Chart waits ~45 min for a free doctor; VTE section then skipped when the take is busy | Prompt line on the clerking proforma | Steps mapped | 0
[8 empty] | Steps flagged as a problem | 0
[8 empty] | Hands-on time, end to end (mins) | 0
[8 empty] | Waiting time, end to end (mins) | 0
Share of the journey spent waiting
A long wait next to a short task is usually where the delay lives — and often the easiest thing to fix.
Draw it as a picture → aimqa.github.io/SAMQIP — the Process Map tab turns these steps into a diagram you can paste into your slides.

## Causes
Causes — what is driving the problem
Stage 2. Draw the fishbone in the tool, then log the causes here. The point of this tab is the evidence column: it separates what you have actually checked from what the team merely suspects.
# | Category | Cause — one line | How do we know? (evidence, or ‘hunch’) | Evidence? | Worth tackling? | Becomes which driver? | AT A GLANCE (updates itself)
EX | Process | Nothing prompts VTE while the chart is written | Watched 6 clerkings; no prompt on the proforma | Checked | Yes | Secondary driver → prompt at the point of prescribing | Causes logged | 0
[7 empty] | Backed by evidence | 0
[7 empty] | Still just a hunch | 0
[7 empty] | Picked to tackle | 0
If everything is a hunch, you are guessing. Go and check two or three before you pick one to change.
Draw the fishbone → aimqa.github.io/SAMQIP — the Fishbone tab turns these causes straight into a driver diagram.

## Data Plan
Data Plan — one outcome, one process, one balancing measure
Stage 2. Define each measure so two people would count it the same way. Small samples are fine: 10–20 cases per time point.
Measure | Type | Operational definition (what exactly counts?) | Data source | Who collects | How often | Target
EXAMPLE — VTE assessment completed | Process | VTE risk assessment completed within 14 h of the decision to admit — counted per 20 charts sampled | Drug charts, AMU | FY1 of the week | Weekly (Mon) | 90% by Mar 2027
Outcome
Process
Balancing
Need the diagrams first? Draw your process map & driver diagram at aimqa.github.io/SAMQIP — then paste the PNGs into your slides.

## Data Log
Data Log — feeds the run chart automatically
One row per week. Enter n and how many met the standard — % calculates itself. Mark the week you launched with ★ INTERVENTION.
Week ending | Cases reviewed (n) | Met standard | % met (auto) | Balancing count | Intervention? | Context note (see Diary)
2026-01-12 | 20 | 12 | 60% | 0 |  | EXAMPLE — baseline week 1

## Diary
Project Diary — the qualitative data
A few lines a week: what changed around you, and what people said. This is what explains the run chart — and where cycle-2 ideas come from.
Date | What happened / what changed around us | Quote or comment (verbatim) | Tag | Logged by
2026-01-15 | EXAMPLE — ward at 110% capacity all week; two escalation beds open | “Nobody restocks the proforma tray at weekends” — Sister J. | Hindered | A. Khan

## PDSA Log
PDSA Log — one row per cycle
Write the prediction BEFORE you launch (Plan), then complete the row as the cycle runs. Cycle 2 should be smaller than cycle 1.
Cycle | Dates (from – to) | PLAN — the change & your prediction | DO — what actually happened | STUDY — what the data showed | ACT — keep / tweak / drop | Next step
EX | 06 Jan – 02 Feb | VTE prompt line on every clerking proforma; predict completion rises 60% → 80% | Launched Monday; night shifts used old proformas in week 1 — old stock withdrawn | Rose to 75% by week 3; dipped every weekend | Tweak — weekend proforma restock added to the ward checklist | Cycle 2 from 09 Feb
1
2
3

## SQUIRE Check
SQUIRE Check — run this before you present or submit
Stage 6. Mark each item Yes / No / N/A — if N/A, justify it in Notes. Home counts the ‘Yes’ rows. Full guidance: the SQUIRE 2.0 Reporting Guide.
# | SQUIRE item | Covered? | Where (slide / section) | Notes / justification
1 | Title — signals an improvement initiative
2 | Abstract — structured & searchable
3 | Problem Description — local nature & significance
4 | Available Knowledge — what’s already known
5 | Rationale — framework, assumptions, mechanism
6 | Specific Aims — of the project & the report
7 | Context — setting described at the outset
8 | Intervention(s) — reproducible detail & team
9 | Study of the Intervention — impact & causality
10 | Measures — outcome, process, balancing
11 | Analysis — quantitative & qualitative
12 | Ethical Considerations — review, harms, COI
13 | Results — evolution, data, context, surprises
14 | Summary — key findings & strengths
15 | Interpretation — meaning, comparison, costs
16 | Limitations — validity & generalisability
17 | Conclusions — usefulness, spread, next steps
18 | Funding — sources & funder role

## Share & Replicate
Share Your QIP — replication pack
Stage 7. The blue boxes fill themselves in from your other tabs — you only write the six white ones in section C. Then File → Print → PDF (set to fit one page) and send it with the three images listed at the bottom.
A WHAT WE DID — fills itself from the Home tab
Project title | ← fill in on Home
Aim (SMART) | ← fill in on Home
Setting it ran in | ← fill in on Home
Quality domain (WHO) | ← pick on Home
Project type | ← pick on Home
B WHAT WE CHANGED, AND WHAT HAPPENED — fills itself from PDSA Log & Data Plan
The change we tested | ← fill in cycle 1 on PDSA Log
What the data showed | ← fill in cycle 1 on PDSA Log
Our verdict | ← keep / tweak / drop, on PDSA Log
Outcome measure | ← fill in on Data Plan
Process measure | ← fill in on Data Plan
Balancing measure | ← fill in on Data Plan
C WHAT YOU’D NEED TO REPEAT IT SOMEWHERE ELSE — the only part you write. Six boxes, a line or two each.
1. Before you start | Who has to say yes (ward manager, pharmacy, IT…), and anything that must already exist — a proforma, a form, system access, a regular meeting.
2. What it actually cost | Money spent (often £0 — say so), plus the honest time: roughly how many hours a week, and from whom.
3. What made it work here | The local conditions that mattered — a supportive pharmacist, a daily board round, a ward small enough to brief in one go. This is what tells someone whether it will transfer.
4. What we’d do differently | The honest bit — what went wrong, what we wasted time on, what we’d skip. Most useful box on the page.
5. Expect to adapt | If your setting differs — electronic rather than paper charts, bigger ward, no pharmacist — change this part.
6. Happy to be asked? | Name and contact email of someone who will answer a question about it — and confirm they’re happy to be contacted.
D SEND THIS WITH IT — three images and this page; nothing else needed
Process map (PNG) | Attached? | From aimqa.github.io/SAMQIP — Download PNG
Driver diagram (PNG) | Attached? | Same tool, Driver Diagram tab
Run chart | Attached? | Copy the chart from the Data Log tab
Write-up (optional) | Attached? | Only if you’ve done one — SQUIRE deck or poster
SQUIRE items covered | 0 of 18 — a write-up is optional; this page is enough to pass the project on.
Send it to: your own QI / clinical audit team, your local QIP team, and the ward you’re passing it to. If it worked, it is worth a regional meeting or BMJ Open Quality — ask your supervisor. No patient-identifiable data on this page, ever.