SOCIETY FOR ACUTE MEDICINE  ·  QUALITY IMPROVEMENT

The QIP Kit — Start Here

Everything you need to run a quality improvement project on the AMU, from first idea to finished write-up. Eight files. This page says which one to open when.

If you only open one thing, open the Roadmap. It is the spine of everything else: seven stages, first idea to finished write-up, and round again. The rest of the kit hangs off those stages.

What each file is for

In the order you are likely to need them.

| FILE | WHAT IT IS | WHEN YOU NEED IT |
| --- | --- | --- |
| QIP Roadmap | A 22-slide deck. The seven stages, with what to do, what is enough, and how you know you are finished at each one. | Read it first, then keep it open beside you. |
| Roadmap poster | The same seven stages on a single page, for the wall. | Print it and put it up in the office. |
| Team Workbook | One Excel file, eleven tabs: the pitch, process map, causes, measures, data log, PDSA cycles, diary, SQUIRE check and a one-page pack for handing the project on. | From day one — this is where the project actually lives. |
| Diagram Tool | A website. Seven tabs: pitch, 2×2 idea sorting, process map, fishbone, 5 Whys, driver diagram, measures. Exports straight into your slides. | Stages 1 and 2, whenever you need to draw something. |
| SQUIRE Reporting Guide | A 19-slide walkthrough of the 18 SQUIRE items in plain English. | Stage 6, when you write the project up. |
| SQUIRE Presentation Template | A 28-slide skeleton with the sections already laid out. Entirely optional. | Only if you want the write-up as slides. |
| SAM Support Network | Where help comes from: a weekly team on your unit, a regional network, and what SAM provides nationally. | When you are stuck, or setting up a unit QI team. |
| Audit Data Template | Patient-level spreadsheet for the before and after groups — demographics, length of stay, mortality, readmission. | Only if your project needs patient-level data. Store on NHS systems only. |

Which file, at which stage

The seven stages of the Roadmap, and what you should have open.

| STAGE | OPEN THIS | YOU ARE DONE WHEN |
| --- | --- | --- |
| 1 Pitch Your QIP | Roadmap · Workbook (Home) · Diagram Tool (Pitch, 2×2) | A consultant has said yes, and you have a named supervisor. |
| 2 Plan Your QIP | Workbook (Process Map, Causes, Data Plan) · Diagram Tool (all seven tabs) | You have a baseline run chart and a one-page data plan. |
| 3 Plan Your Intervention | Workbook (Actions Log) | The team knows the plan and the start date is in the diary. |
| 4 Deliver & Measure | Workbook (Data Log, Diary, PDSA Log) | 6–8 post-change data points and a diary of what really happened. |
| 5 Present Your Data | Workbook (Data Log chart) | The team has seen the chart and agreed what happens next. |
| 6 The SQUIRE Write-Up | Reporting Guide · Workbook (SQUIRE Check) · Template if you want it | All 18 items ticked or justified, and submitted. |
| 7 Repeat the Cycle | Workbook (Share & Replicate) | The next cycle has an owner and a start date — even if it is not you. |

If you are starting this week

1. Find a problem that bugs you. 2. Count something — 20 sets of notes is enough. 3. Book a pitch slot at the next QIP meeting.

That is genuinely the whole of Stage 1. Everything else in this kit exists to support what happens after you have done those three things.

For whoever looks after the kit

- The Diagram Tool is a website: aimqa.github.io/SAMQIP  — it is one HTML file, hosted on GitHub Pages. Nothing to install.

- Everything in it saves automatically in the browser. Sharing a link, live collaboration and sign-in-to-sync are optional extras.

- COLLABORATION_SETUP.md and firebase-rules.json cover those extras. Nobody using the kit day to day needs to read either.

- No patient-identifiable data anywhere in the kit — count, do not name. That rule holds in the workbook, the tool and anything shared.

One shared file, not one each The Team Workbook is designed to be a single shared file for the whole project — on the team drive or in Teams, with everyone editing the same copy. Emailing copies around is how projects end up with three different versions of the truth.