## Slide 1
7 STAGES · 1 CYCLE
SOCIETY FOR ACUTE MEDICINE · QUALITY IMPROVEMENT
The QIP Roadmap
Seven stages from first idea to finished write-up — and round again.
Works with the SQUIRE 2.0 Presentation Template and Reporting Guide — Stage 6 hands you over to them.
Society for Acute Medicine | Quality Improvement

## Slide 2
The Seven Stages at a Glance
01
Pitch Your QIP
Sell the problem in five sentences
An approved idea
02
Plan Your QIP
Process map, driver diagram, data plan, baseline
Baseline run chart
03
Plan Your Intervention
Your quick-win idea, ready to test
A start date
04
Deliver & Measure
Run the change; keep the data coming
Post-change data
05
Present Your Data
One run chart, three messages
A team decision
06
SQUIRE Write-Up
Guide first — Template optional
A finished report
07
Repeat the Cycle
Back to Stage 3 — smaller and sharper
Cycle 2 owner
One loop = one PDSA cycle. Stages 1–3 are Plan, 4 is Do, 5 is Study, 6–7 are Act.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Overview of the seven-stage QIP journey: pitch, plan, plan the intervention, deliver and measure, present, SQUIRE write-up, repeat. Right column shows the output of each stage.

## Slide 3
STAGE 1 — SETTLE THIS BEFORE YOU PITCH ANYTHING
QI, Audit or Research?
STAGE 1
Quality improvement
“How do we improve how we do it here?”
Testing local changes and measuring the effect — this Roadmap.
Register with your trust’s clinical audit / QI team. No ethics committee needed.
Clinical audit
“Are we meeting the standard?”
Measuring current practice against an agreed standard — no change being tested.
Register with the clinical audit team. No ethics committee needed.
Research
“What should best practice be?”
Creating new, generalisable knowledge — hypotheses, controls, publication beyond your ward.
Needs HRA / Research Ethics approval BEFORE you start — speak to the R&D office.
Rule of thumb: changing something and measuring it locally = QI. Not sure? hra-decisiontools.org.uk/research decides it in five clicks.
Information governance — whichever label: count, don’t name. No patient-identifiable data in workbooks, e-mails or on personal devices. If you genuinely need identifiers, use trust systems only — and ask your IG team first.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Opens Stage 1 — the QI / clinical audit / research distinction (HQIP guidance): QI tests local change (register with the audit/QI office, no REC); audit measures against a standard (register, no REC); research creates generalisable knowledge and needs HRA/REC approval before starting. The HRA decision tool at hra-decisiontools.org.uk/research settles borderline cases. Settling the label first avoids the classic novice error of collecting data for months and then discovering the project needed approval. Information governance applies to all three: no patient-identifiable data outside trust systems; count, don’t name; involve the IG team if identifiers are genuinely needed.

## Slide 4
STAGE 1 OF 7 — PLAN
Pitch Your QIP
STAGE 1
What to do
Spot a problem that bugs you (and your team) day to day
Count something — 20 sets of notes or one week of data
Draft a one-line aim: from [X] to [Y] by [date] — targeting a WHO quality domain (safe, timely, effective…)
Find a consultant supervisor and a friend to share the work
Check who needs to be on board — and talk to them before you pitch
Pitch it in five sentences: problem · number · aim · why it matters · the ask — worked example follows
What’s enough
Five sentences and one honest local number. Three change ideas, sorted on a quick 2×2 — no scoring needed.
You’re done when…
A consultant has said ‘yes, go ahead’ — and you have a named supervisor.
FEEDS SQUIRE ITEMS 3 · 4 · 6 — see the Reporting Guide for each. WHO quality domains → who.int
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Stage 1 (Plan): identify a local problem, quantify it simply, draft an aim targeting a WHO quality domain (who.int/health-topics/quality-of-care), check stakeholders (who must say yes), secure a supervisor, then pitch in five sentences: problem, one honest number, the aim, why it matters, the ask. Keep one-line answers to the four audience questions (What is it? How does it work? Can you back it up? Can you do it?) ready for the Q&A. Change ideas are sorted on a simple impact × ease 2×2 — quick wins first. Feeds SQUIRE items 3, 4, 6.

## Slide 5
STAGE 1 CONTINUED — THE PITCH, KEPT SMALL
The Five-Sentence Pitch
STAGE 1
1
The problem
What’s going wrong, for which patients — as you’ve seen it on the ward.
2
The number
One honest local figure: “12 of 20 charts last week.” No literature review.
3
The aim
From [X] to [Y] by [date].
4
Why it matters
The WHO quality domain it targets — and what it means for patients.
5
The ask
A named supervisor — and a ‘yes, go ahead’ to collect baseline data.
IN YOUR BACK POCKET
The four questions the room will ask:
“What is it?”
“How does it work?”
“Can you back it up?”
“Can you do it?”
Have a one-line answer to each — in your head, not in the script.
YOUR PITCH FEEDS FORWARD The aim starts Stage 2’s driver diagram — and your change ideas get sorted two slides on.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Stage 1 supplement — the five-sentence pitch (problem, number, aim, why it matters, ask). This replaces the longer scripted four-part structure as the core path, in line with BMJ guidance that an aim-based elevator pitch is a lightweight persuasion step, not a scripted speech; the four audience questions (What is it? How does it work? Can you back it up? Can you do it?) are kept as Q&A preparation rather than sentence budgets. Feeds SQUIRE items 3, 4 and 6.

## Slide 6
STAGE 1 WORKED EXAMPLE — THE IDA PITCH IN FIVE SENTENCES (ANONYMISED)
Five Sentences, Written Out
STAGE 1
1. Iron-deficiency anaemia is one of our commonest SDEC presentations — and getting the work-up wrong risks missing a malignancy.
2. Last month, fewer than half of our IDA patients had the underlying cause investigated before discharge.
3. We aim to increase appropriate IV iron use by 25% — and cut inappropriate transfusions by 90% — within 12 months.
4. That’s safer, more effective care: fewer patients exposed to transfusion risk, fewer reattending for infusions they didn’t need.
5. Dr [supervisor] has agreed to supervise — we’re asking for the go-ahead to collect baseline data.
WHY IT WORKS
Opens on a risk that matters — missed malignancy
One honest local number — no literature review in sight
The aim has an X, a Y and a date
‘Why it matters’ names the WHO domains: safe, effective
Ends on a clear, small ask — a supervisor and a go-ahead
Keep the fuller answers — delivery plan, measures, feasibility — in your back pocket for the questions afterwards.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Stage 1 worked example — the department’s iron-deficiency anaemia pitch condensed to the five-sentence form (anonymised). Sentence 1 problem, 2 local number, 3 SMART aim, 4 why it matters (WHO domains safe and effective), 5 the ask. Delivery plan, the three measure types and feasibility remain Q&A material rather than scripted content.

## Slide 7
STAGE 1 CONTINUED — CHOOSING WHAT TO TEST FIRST
Sort Your Ideas on a 2×2
STAGE 1
IMPACT →
EASE OF DELIVERY →
QUICK WINS — START HERE
big bets — later cycles
park these
easy, but low yield
IDA pathway
ePrescribing prompt
One-off high-dose approval
Education sessions
Posters
HOW TO USE IT
Sticky notes on a whiteboard — two minutes per idea, with the team
Ask of each: how much would it move the aim? Could WE deliver it this rotation?
No scores needed — where it sits relative to the others is enough
Pick ONE from the top-right for cycle 1; park the rest for later cycles
These five are from the IDA pitch — the pathway wins: high impact, deliverable this rotation.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Stage 1 supplement — sorting change ideas on a simple impact × ease-of-delivery 2×2 (the beginner prioritisation matrix recommended by NHS QSIR / NHS Education for Scotland) rather than a 0-5 scored table. Quick wins (top-right: high impact, easy to deliver) go first; big bets wait for later cycles; easy-but-low-yield and hard-low-impact ideas are parked. Example placement uses the anonymised IDA pitch ideas: the pathway is the quick win.

## Slide 8
STAGE 1 CONTINUED — BEFORE YOU PITCH
Who Needs to Be On Board?
STAGE 1
Who does the work day-to-day?
Nurses, HCAs, pharmacists, ward clerks — the people your change actually lands on. Invite one onto the team.
Whose sign-off do you need?
Ward manager, clinical lead, pharmacy, IT — name them before you launch. Nothing stalls a first QIP like a missing ‘yes’.
Who might resist — and why?
It’s usually workload, not obstinacy. Ask what would make the change easier before you start, not after.
Who speaks for patients?
Even one conversation — or a PALS / friends-and-family theme — counts. Note what patients say about the problem.
Buy-in is the commonest reason first QIPs stall. A five-minute corridor conversation now saves a stalled launch later — there’s a ‘who must say yes’ line on the Team Workbook’s Home tab.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Stage 1 supplement — stakeholder and patient-voice check before pitching, reflecting BMJ guidance that stakeholder buy-in is the factor without which a QIP is likely to fail regardless of the idea’s quality. Four prompts: who does the work day-to-day (invite one onto the team); whose sign-off is needed; who might resist and why (usually workload); who speaks for patients (a single conversation or PALS/FFT theme is enough for a first project). A matching field exists on the Team Workbook Home tab.

## Slide 9
STAGE 2 OF 7 — PLAN
Plan Your QIP
STAGE 2
What to do
Map the current process with the people who do the work — log it on the Workbook’s Process Map tab
Fishbone the causes, then 5 Whys the ones you can evidence
Sketch a driver diagram: aim → primary → secondary → change ideas — see ‘Primary vs Secondary Drivers’
Pick measures: one outcome, one process, one balancing
Write a data plan: what, who collects, how often, recorded where
Collect 2–4 weeks of baseline before changing anything
Register the project with your trust’s audit team first
What’s enough
Photos of a sticky-note process map and a whiteboard driver diagram — tested against the WHO quality lens. Baseline of 10–20 cases per week.
You’re done when…
You have a baseline run chart and a one-page data plan.
Draw both online → aimqa.github.io/SAMQIP
FEEDS SQUIRE ITEMS 5 · 7 · 10 · 12 — see the Reporting Guide for each.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Stage 2 (Plan): process map, driver diagram, choose the three measure types, write the data plan, collect baseline, register with the trust audit team. Both diagrams can be drawn and exported in the SAM QIP Diagram Tool at https://aimqa.github.io/SAMQIP/ (includes the WHO quality lens and a worked VTE example). Feeds SQUIRE items 5 (Rationale), 7 (Context), 10 (Measures), 12 (Ethics).

## Slide 10
STAGE 2 CONTINUED — BEFORE YOU CAN CHANGE IT, YOU HAVE TO SEE IT
Map What Actually Happens
STAGE 2
Patient arrives on AMU
Clerked by admitting doctor
VTE section done?
Wait for the drug round
First doses given
15 min
waits 2 h
Pill start / end Box a step Diamond a decision — map the ‘no’ route too Dashed a wait or delay
How to do it
Walk the route with the people who do the work — not from memory at a desk
Thirty minutes and a corridor conversation is enough
Map what actually happens, including the workarounds — not what the policy says
Stop at 8–12 steps: any more and you’re mapping the hospital, not the problem
What you’re looking for
The waits between steps — that’s usually where the delay really lives
The steps where it goes wrong: those become your change ideas
Steps two people describe differently — that disagreement is a finding in itself
Anything done twice, or not at all
Log the detail on the Workbook’s Process Map tab — who does each step, how long it takes, how long people wait, what goes wrong. Then draw the picture: aimqa.github.io/SAMQIP
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Stage 2 supplement — process mapping. Walk the route with the people who do the work rather than reconstructing it at a desk; thirty minutes is usually enough; map what actually happens including workarounds, not the policy; stop at 8-12 steps. What to look for: the waits between steps (usually the bulk of the patient journey — the worked example shows a 15-minute task followed by a two-hour wait), the steps where things go wrong (these become change ideas), steps that two people describe differently, and anything done twice or not at all. The four shapes match the Diagram Tool: pill for start/end, box for a step, diamond for a decision (map the 'no' route too), dashed for a wait. Detail goes on the Team Workbook's Process Map tab, which totals hands-on versus waiting time; the picture is drawn at aimqa.github.io/SAMQIP. Feeds SQUIRE item 7 (Context).

## Slide 11
STAGE 2 CONTINUED — GET EVERY CANDIDATE CAUSE OUT ON THE TABLE
Fishbone: Spread Wide Before You Go Deep
STAGE 2
VTE assessment
missed at clerking
People
New F1s never shown the box
Locums don’t know our proforma
Process
Nothing prompts it at the chart
No check before post-take
Equipment
Proforma predates the rule
Environment
Noisy bay, interruptions
Worst at weekends
Policies
Nobody knows the 14-hour target
Patient factors
No weight → dose left blank
Why bother, when you have the 5 Whys?
The 5 Whys goes deep down one path — the fishbone goes wide across all of them
It stops the team fixing the first cause somebody happens to name
The empty bones are informative too: they show where nobody has looked
How to run it in twenty minutes
Problem in the head on the right — one sentence, no blame
Take each bone in turn: “what here could be contributing?”
Write everything down first; argue about importance afterwards
Then pick the one or two you have evidence for, and take those deep
Draw it online — the Fishbone tab at aimqa.github.io/SAMQIP turns your causes straight into a driver diagram, and the Workbook’s Causes tab is where you record which ones you actually have evidence for.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Stage 2 supplement — the fishbone (Ishikawa / cause-and-effect diagram). Its job is breadth: get every candidate cause out of people's heads before the team starts arguing about which one matters. That is the opposite of the 5 Whys, which takes a single path and drills down; the two are complementary and the usual order is fishbone first, then 5 Whys on the one or two causes you have evidence for. Six categories are offered as a prompt — People, Process, Equipment, Environment, Policies, Patient factors — and teams should rename any that do not fit, and leave a bone empty rather than inventing a cause to fill it. An empty bone is itself a finding: it usually means nobody has looked there. Run it as a twenty-minute whiteboard exercise with the people who do the work. Causes then become secondary drivers on the driver diagram — the Diagram Tool does that transfer in one click. Feeds SQUIRE item 7 (Context) and item 5 (Problem description).

## Slide 12
STAGE 2 CONTINUED — BEFORE YOU DRAW THE DRIVER DIAGRAM
First, Ask Why — Five Times
STAGE 2
THE PROBLEM VTE assessments get missed at clerking
↓ why?
WHY 1 Doctors skip the section when it’s busy
↓ why?
WHY 2 Nothing prompts it while the chart is being written
↓ why?
WHY 3 The clerking proforma predates the VTE requirement
↓ why?
ROOT CAUSE A process gap — not a people problem. Fix the proforma.
HOW TO DO IT
Ten minutes at the whiteboard, with the team — three to five whys is typical
Keep asking until you hit something you can redesign: a process, a form, a step — not a person
If your final ‘why’ names a person, ask why once more
The root cause becomes a secondary driver — its fixes become your change ideas
Draw it online → aimqa.github.io/SAMQIP — the Diagram Tool has a 5 Whys tab between the process map and driver diagram.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Stage 2 supplement — a simple 5 Whys before the driver diagram, as recommended for novices by the BMJ getting-started guide, RCS England trainee guide, RCP and IHI (fishbone is the heavier alternative). Worked VTE chain: problem → skipped when busy → no prompt at the point of writing → proforma predates the requirement → root cause is a process gap. Teaching points: stop at a system cause you can redesign; blame the process, not the people; the root cause feeds the driver diagram as a secondary driver. The Diagram Tool at aimqa.github.io/SAMQIP includes a 5 Whys builder.

## Slide 13
STAGE 2 CONTINUED — GETTING THE MIDDLE TWO COLUMNS RIGHT
Primary vs Secondary Drivers
STAGE 2
Primary drivers — the headings of your theory
The 3–5 big things that must be true for the aim to happen.
Write them as conditions, not actions — ‘it’s easy to do in the moment’, not ‘put up a poster’.
Common ones: people know what’s expected · it’s easy to do · the team sees its own data · someone owns it.
Test: if all of these were true, would we hit the aim?
Secondary drivers — the bits you can actually get at
The specific parts of the system that would make one primary driver true.
Ward-level and concrete enough to influence — a step, a form, a conversation, a rota.
1–3 under each primary driver is plenty on a first project.
Test: if we changed this, would the driver to its left improve?
AIM
Increase completed VTE assessments on AMU from 60% to 90% by Mar 2027
→
PRIMARY DRIVER
It’s easy to do in the moment
→
SECONDARY DRIVER
Prompt at the point of prescribing
→
CHANGE IDEA
VTE prompt on the clerking proforma
Read it left to right as one sentence: we’ll achieve the aim BECAUSE this driver changes — which will change BECAUSE of this secondary driver — which we’ll test with this change idea.
Three things that catch people out: 1. If it names a poster, checklist or proforma, it’s a change idea — not a driver. 2. If nobody could disagree with it, it’s too vague to be a driver. 3. More than five primary drivers usually means some are really secondary ones.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Stage 2 supplement — primary vs secondary drivers. Primary drivers: the 3-5 big conditions that must be true for the aim to be achieved; written as states, not actions; test by asking whether the aim would follow if all were true. Secondary drivers: the specific, ward-level parts of the system that would make one primary driver true; 1-3 under each primary is enough on a first project; test by asking whether changing it would improve the driver to its left. Change ideas name the artefact or action to test in a PDSA cycle. Common errors: change ideas written in the driver columns; drivers so bland nobody could disagree; too many primary drivers. The same guidance is built into the SAM QIP Diagram Tool at https://aimqa.github.io/SAMQIP/.

## Slide 14
STAGE 2 CONTINUED — WHAT DATA DO YOU NEED?
Two Kinds of Data — You Need Both
STAGE 2
Quantitative — the numbers
WHAT IT IS
Things you can count: rates, percentages, times, simple tallies.
e.g. % of drug charts with a VTE assessment · minutes to antibiotics · falls per week
WHY IT MATTERS
Shows whether things actually changed — plotted over time on your run chart
Convinces others — a chart beats an anecdote in any meeting
Small counts are fine: 10–20 cases per time point, plotted honestly
Qualitative — the words
WHAT IT IS
What people say and experience: comments, quotes, what you observe.
e.g. a huddle comment · a free-text survey box · what you noticed on the ward round
WHY IT MATTERS
Tells you WHY the numbers moved — what helped, what got in the way
Catches what numbers miss — workload, morale, unintended effects
Shapes cycle 2 — the best next change ideas come from what staff tell you
You need both. Numbers show whether it changed — words tell you why. A run chart plus three staff quotes is a complete data set for a first QIP.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Stage 2 supplement: quantitative data (counts, rates, times) show whether performance changed and are plotted over time on the run chart; qualitative data (staff and patient comments, observations) explain why change happened, surface workload and unintended effects, and generate cycle-2 change ideas. Both feed SQUIRE items 10 (Measures) and 11 (Analysis).

## Slide 15
STAGE 3 OF 7 — PLAN
Plan Your Intervention
STAGE 3
What to do
Pick ONE change idea — top-right of your 2×2: high impact, easy to deliver
Design it small: a checklist, proforma prompt or 5-minute teaching
Agree who does what, from what date
Tell everyone affected before you start — huddle, poster, ward meeting
Write down what you predict will happen
What’s enough
One change, one ward, a named start date. If it needs a committee, it’s too big for cycle 1.
You’re done when…
The team knows the plan and the start date is in the diary.
FEEDS SQUIRE ITEMS 8 · 9 — see the Reporting Guide for each.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Stage 3 (Plan): select the quick-win change idea (top-right of the Stage 1 2×2 — high impact, easy to deliver), design it small, assign roles and a start date, communicate, record a prediction. Feeds SQUIRE items 8 (Intervention) and 9 (Study of the Intervention).

## Slide 16
STAGE 4 OF 7 — DO
Deliver & Measure
STAGE 4
What to do
Launch on the planned date — be visible in week one
Keep collecting the same measures, the same way, every week
Keep a project diary — tweaks made, and what changed around you
Don’t panic at a dip — the next slide shows what counts as a signal
Run for 6–8 weeks after the change
What’s enough
Same counting rules as baseline, plus a few diary lines a week.
You’re done when…
You have 6–8 post-change data points and a diary of what really happened.
FEEDS SQUIRE ITEMS 10b–c · 13a — see the Reporting Guide for each.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Stage 4 (Do): launch, keep measuring identically, keep a context diary, continue 4-8 weeks. Feeds SQUIRE items 10b-c (context tracking, data quality) and 13a (evolution).

## Slide 17
STAGE 4 CONTINUED — SIGNAL OR NOISE?
How to Read Your Run Chart
STAGE 4
median
↓ change launched
astronomical point — a story, not a signal
SHIFT — 6+ in a row above the median
(example: % of drug charts with VTE assessment completed — rising after launch)
Shift
6 or more consecutive dots on the same side of the median — that’s a real change.
Trend
5 or more dots all rising, or all falling — drift, in either direction.
Astronomical point
One wildly different dot. Check the diary for the story — don’t change course on it.
Annotate everything, react to almost nothing. Mark the launch, staffing changes, winter pressures on the chart — and never change course on a single dot. Aim for 10–12 dots before calling anything.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Stage 4 supplement — minimal run-chart interpretation for novices (IHI QI104 rules; RCS England trainee-guide appendix): a shift is six or more consecutive points on one side of the median; a trend is five or more consecutive points all increasing or decreasing; an astronomical point is a single data point far from the rest — investigate via the project diary rather than reacting. Annotate the chart with the launch date and context events; do not react to single points; roughly 10-12 points are needed before drawing conclusions. This is deliberately NOT full SPC — control charts stay out of a first project.

## Slide 18
STAGE 5 OF 7 — STUDY
Present Your Data
STAGE 5
What to do
Plot baseline and post-change on ONE run chart — arrow at the change
Add the headline: before vs after, against your aim
Say what surprised you, what helped, what got in the way
Present for ten minutes at the QIP or governance meeting
Ask the room: keep, tweak or drop the change?
What’s enough
One Excel run chart and three messages. Honest beats impressive.
You’re done when…
The team has seen the chart and agreed what happens next.
FEEDS SQUIRE ITEMS 11 · 13 — see the Reporting Guide for each.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Stage 5 (Study): one combined run chart, headline result, surprises and context, 10-minute presentation, team decision. Feeds SQUIRE items 11 (Analysis) and 13 (Results).

## Slide 19
STAGE 6 OF 7 — ACT
The SQUIRE Write-Up
STAGE 6
What to do
Start with the Reporting Guide — ‘what’s enough’ for each of the 18 items
Want fill-in slides? The Presentation Template is optional — use only the ones you need
Write the title and abstract last
Run the 18-item self-check on the final slide
Submit it somewhere: local QIP day, regional meeting, poster
What’s enough
A few honest sentences per item — SQUIRE itself says skip what doesn’t apply (and say why).
You’re done when…
All 18 items ticked (or justified) — and it’s submitted.
FEEDS SQUIRE ITEMS 1–18 — this stage is the Reporting Guide.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Stage 6 (Act): work through the Reporting Guide (what’s enough per item); the fill-in Presentation Template is an optional aid — SQUIRE 2.0’s own authors advise omitting items where inappropriate, with justification. Title and abstract last; run the 18-item self-check; submit. Covers SQUIRE items 1-18.

## Slide 20
STAGE 7 OF 7 — ACT → PLAN
Repeat the Cycle
STAGE 7
What to do
Ask: what would we change after cycle 1?
Adjust the intervention — or try the next driver
Go round again from Stage 3 — the planning is already done
Rotating on? Hand over the data plan, diary and run chart
Think spread: could the next ward try it?
Fill in the Workbook’s Share & Replicate tab — one page, mostly auto-filled
What’s enough
Cycle 2 is smaller than cycle 1 — you’re refining, not restarting. One page is enough to pass it on.
You’re done when…
The next cycle has an owner and a start date — even if it isn’t you.
FEEDS SQUIRE ITEMS 17 — next steps, spread, sustainability.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Stage 7 (Act): learn from cycle 1, adjust, loop back to Stage 3, hand over properly if rotating, consider spread. To pass the project to another ward or trust, complete the Share & Replicate tab in the Team Workbook: sections A, B and D fill themselves from Home, PDSA Log, Data Plan and SQUIRE Check, so the team only writes six boxes — prerequisites, real cost in time, what made it work locally, what they’d do differently, what to adapt elsewhere, and a contact. It prints to a single page and travels with the two diagram PNGs and the run chart. Feeds SQUIRE item 17 (Conclusions and next steps).

## Slide 21
OPTIONAL EXTRA — FOR WHEN YOU PRESENT YOUR WORK (STAGE 5 ONWARDS)
Bringing a Presentation to Life
OPTIONAL
The pitch itself stays five plain sentences. But when you present the finished work, three story moves lift a talk:
The Opening — your reason for being
One or two sentences on the moment this problem got under your skin — your ‘aha’ moment.
“The third time I watched a patient reattend for an infusion they didn’t need, I started counting.”
The Callback
Later in the talk, return to that opening with a short anecdote that confirms it.
“Remember that third patient? She’s why the pathway carries a reattendance measure.”
The ‘All Is Lost’ Moment
Name the problem that nearly sank — or still threatens — the project, then how you’ll overcome it.
“Pharmacy sign-off stalled for a month — so we took it to the joint medicines committee.”
Save these for Stage 5 and beyond. “What is it?” and “How does it work?” are still what the room decides on — the story moves make the answers land.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Optional appendix (moved out of the Stage 1 core path per benchmarking against BMJ/RCS England beginner guidance) — presentation storytelling, from the AIM pitch guidance: (1) Opening / reason for being — one or two sentences on the aha moment that made you invested; (2) Callback — return to the opening later with an anecdote that confirms it; (3) All-is-lost moment — the problem that jeopardised (or jeopardises) the project and how you overcame or plan to overcome it. About 25 sentences in logical order makes a serviceable three-minute pitch; the first two questions (What is it? / How does it work?) are the most essential and deserve the most attention. Illustrative quotes are fictional examples in the style of the IDA worked example.

## Slide 22
A REALISTIC TIMETABLE — STRETCH OR SHRINK TO FIT
Fits a Four-Month Rotation
1
Pitch
Weeks 1–2
2
Plan & baseline
Weeks 3–6
3
Plan the change
Week 7
4
Deliver & measure
Weeks 8–13
5–6
Present & write up
Weeks 14–16
The numbers are the stages — Stage 7 (repeat the cycle) is the next cycle, or your handover.
Rotating on before it’s finished?
Stage 7 becomes a handover: pass on the data plan, the diary and the run chart to a named person. A properly handed-over QIP is a completed stage — not an unfinished project.
Most first QIPs fit one rotation — cycle 2 often belongs to the next trainee.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap
Notes: Suggested pacing across a four-month rotation: pitch (wks 1-2), plan and baseline (3-6), plan the change (7), deliver and measure (8-13), present and write up (14-16). Handover guidance for trainees rotating on.

## Slide 23
Start this week.
1
Find a problem that bugs you
2
Count something — 20 sets of notes is enough
3
Book a pitch slot at the next QIP meeting
Every finished QIP started exactly here. Questions? Speak to your local QIP team.
Society for Acute Medicine | Quality Improvement
SAM QIP Roadmap